## Slide 1
Small Works Contracting
Mission
GA helps its customers succeed
Vision
Customers seek and value our services and expertise
Others recognize our innovation and efficiency.
People want to work here.
John Lynch and Roland Orr
State of Washington
Division of Engineering and Architectural Services

## Slide 2: Division of Engineering and Architectural Services
Design and Construction Project Management
Energy Performance Contracting
We serve a number of major state agencies
  Community Colleges - 33 campuses
  Department of Corrections
  Department of Social and Health Services
  Department of Veterans Affairs
  Washington State Patrol
  Department of General Administration
  Approximately 20 additional small agencies

## Slide 3: Objectives for Today
Demonstrate examples showing when to follow a public works procurement process vs. a purchasing process
Outline the general differences in the public works process depending on the size and nature of the project
Discuss the “Limited Public Works” process used by the Department of General Administration for small public works projects

## Slide 4: Characteristics of Public Works
Work is performed on public property
Work is more than “ordinary maintenance”
Work tends to require a building permit
Cost of labor is a significant portion of the total cost of the work
The level of the project cost and the source of project funding are not factors that determine public works

## Slide 5: State Statute References
RCW 39.04 Public Works
RCW 39.06 Licensed Contractors Required
RCW 39.10 Alternative Public Works
RCW 39.12 Prevailing Wages
RCW 39.80 Architect/Engineering Contracts
RCW 43.19 General Administration
RCW 60.28 Liens for labor, taxes, etc.
RCW 39.34 Inter-local Cooperation Act
RCW 28A School Districts
RCW 35 Counties
RCW 36 Cities

## Slide 6: Example Project #1

## Slide 7: Example Projects
  Number 1
  Convert an existing classroom into four individual private offices. Build framed walls, provide new lighting & receptacles, modify existing HVAC, modify fire alarm system, and carpet etc.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 8: Example Projects
  Number 1
  Convert an existing classroom into four individual private offices. Build framed walls, provide new lighting & receptacles, modify existing HVAC, modify fire alarm system, and carpet etc.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 9: Example Project #2

## Slide 10: Example Projects
Number 2
Replace an existing rooftop HVAC unit. The existing electrical wiring can be re-used and the existing ductwork should match with only minor modifications.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 11: Example Projects
Number 2
Replace an existing rooftop HVAC unit. The existing electrical wiring can be re-used and the existing ductwork should match with only minor modifications.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 12: Example Project #3

## Slide 13: Example Projects
Number 3
Replace an large existing rooftop HVAC unit. New electrical wiring may be needed and the existing ductwork will need modifications. The new unit may be heavier.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 14: Example Projects
Number 3
Replace an large existing rooftop HVAC unit. New electrical wiring may be needed and the existing ductwork will need modifications. The new unit may be heavier.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 15: Example #4

## Slide 16: Example Projects
Number 4
Repaint a two story building.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 17: Example Projects
Number 4
Repaint a two story building.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 18: Example #5

## Slide 19: Example Projects
Number 5
Provide new carpet in a 20,000 sq. foot office building.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 20: Example Projects
Number 5
Provide new carpet in a 20,000 sq. foot office building.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 21: Example Project #6

## Slide 22: Example Project #6

## Slide 23: Example Projects
Number 6
  Provide a thin sealer coat and new paint striping for an asphalt parking lot.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 24: Example Projects
Number 6
  Provide a thin sealer coat for an asphalt parking lot.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 25: Example Project #7

## Slide 26: Example Projects
Number 7
  Provide new asphalt paving for a parking lot.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 27: Example Projects
Number 7
  Provide new asphalt paving for a parking lot.
  Which procurement process should be used?
   Public Works process
   Purchasing process

## Slide 28: Example #8

## Slide 29: Example Projects
Number 8
  A civic organization has offered build a commemorative memorial with landscaping at a state facility campus.
  Which procurement process should be used?
   Public Works process
   Purchasing process
   Neither

## Slide 30: Example Projects
Number 8
  A civic organization has offered build a commemorative memorial with landscaping at a state facility campus.
  Which procurement process should be used?
   Public Works process
   Purchasing process
   Neither

## Slide 31: Example Projects
RCW 39.04.010 Definitions
The term public work shall include all work, construction, alteration, repair, or improvement other than ordinary maintenance, executed at the cost of the state or of any municipality, …...

## Slide 32: The Ideal World
Purchasing Process | Public Works Process

## Slide 33: The Real World
Purchasing Process | Gray Area | Public Works Process

## Slide 34: Purchasing Process
State agencies typically have delegated purchasing authority up to $10,000
Higher Ed has independent authority
Refer to the Washington Purchasing Manual:
  http://www.ga.wa.gov/PCA/Manual.htm

## Slide 35: Public Works Process
Limited Public Works
Small Works Roster
Job Order Contracts
Advertised Projects
Other Alternative Processes for >$10 M
  General Contractor/ Construction Manger
  Design - Build

## Slide 36: Small Works Roster
RCW 39.04.155
Small Works Roster - - Procedure for securing quotations:
Construction, repair, or alteration projects estimated to cost less than two hundred thousand dollars are exempt from the requirement that the contracts be awarded after advertisement and competitive bid as defined by RCW 39.04.010.

## Slide 37: Limited Public Works
A Manual describing the Limited Public Works Process is available on line:
  http://www.ga.wa.gov/eas/doc-form.htm
Forms referenced in the manual are available at the same site.

## Slide 38: Limited Public Works
Limited Public Works is a process used for projects less than $35,000. RCW 39.04.155 allows us to solicit contractors through the Small Works Roster without a public advertisement since the cost is less than $35,000.

## Slide 39: Limited Public Works
Architect/Engineer Contract Services
  A/E is selected based on qualifications per RCW 39.80
  E&AS maintains on-call A/E contracts that are available for state agencies to use
Some LPW projects will not require an A/E contract for the design

## Slide 40: Limited Public Works
Assemble Bid Package Including:
    Cover Sheet w/project number, title and location
    Table of Contents
    Request for Bids
    General Conditions (May be referenced in the specification if available for Contractor review)
    Bid Proposal Form
    Technical Specification w/ Detailed Project Scope of Work
    Applicable Drawings

## Slide 41: Limited Public Works
Compile a list of capable, licensed, contractors utilizing the Small Works Roster
  Notify contractors located within your region with the applicable specialty
  Consider MBE and WBE contractors
Send Bid Packages to interested contractors with notice of pre-bid meeting time and date
Hold a Pre-Bid meeting

## Slide 42: Limited Public Works
Compile contractors Q&A into an addendum to the contract documents
Distribute the addendum to all contractors who received a bid package
Receive and open bids
  Record date, time, and initials on bid envelopes
  Open bids with at least two staff
  Record bids on bid summary sheet

## Slide 43: Limited Public Works
Notify all bidders of the bid results
Prepare LPW Contract
    Check Contractor is licensed (call L & I Contractor Registration (360) 902-5202)
    Contract w/Bond Waiver/Bond Form/Insurance Certificate and/or Retainage Bond Form
    Letter of Transmittal
    Retainage Investment Form
    Transmittal to Insurance Agent attach Certificate of Ins. Form, Insurance Req., and Bond Form

## Slide 44: Limited Public Works
Send contract to contractor
Receive contract back from contractor
Verify that contract requirements have been met
    No changes to document have been made by contractor
    Contract is signed
    Insurance coverage is on State Certificate
    Insurance certificate shows required coverage

## Slide 45: Limited Public Works
Verify contract req. (cont.)
    Insurance Effective Dates cover contract period
    Insurance Company is recognized by the Office of the Insurance Commissioner (phone (360) 753-7307)
    Payment & Performance Bond Waiver is signed/or Payment & Performance Bond is provided/ and Retainage Bond Form if desired

## Slide 46: Limited Public Works
Contracting Officer signs contract
Issue the Notice to Proceed
  Send contractor NTP transmittal
  Send invoice voucher forms
  Send L&I the Notice of Award
If a Change Order is needed, follow the contract requirements

## Slide 47: Limited Public Works
Process Contractors invoice
  A copy of the L&I Intent to Pay Prevailing Wages form to be received with first invoice
  Verify/approve the percent complete on the contractors schedule of values
  Approve the invoice and arrange for payment

## Slide 48: Limited Public Works
Conduct final walk-thru of project
  Create punch list if necessary
  Verify that punch list items are corrected
  Establish the contract acceptance date
  Issue acceptance letter
Send Notice of Completion Form
  For contracts less than $20,000, send directly to Employment Security
  For contracts over $20,000, send to Dept. of Revenue

## Slide 49: Limited Public Works
Final Payment
    Lien period has expired (45 days from the Acceptance Date)
    Receive Affidavit of Wages Paid from Contractor
    Receive release from L & I
    Receive release from Employment Security
    Receive release from Dept. of Revenue for contracts over $20,000
  Release the contract retainage

## Slide 50: Limited Public Works
QUESTIONS ?

## Slide 51: Limited Public Works
Important Telephone Numbers
  E&AS Contracts Section (360) 902-7272
  L&I Contractor Registration (360) 902-5202
  L&I Contracts Release (360) 902-4764
  Employment Security (360) 902-9626
  Dept. of Revenue (360) 753-3830

## Slide 52: Division of Engineering and Architectural Services
Please contact us if you have additional questions or want copies of our standard documents
  jlynch@ga.wa.gov
  rorr@ga.wa.gov